## TMI
Приложение №2 к договору №_____________________от "_______"__________________2019г.
Н
Календарный график производства работ
Месяц |  |  | Октябрь | [22 empty] | Ноябрь
№п/п | Наименование этапов работ | Календарная | 41 |  |  |  |  | 42 | [6 empty] | 43 | [6 empty] | 44 | [6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48
|  | Дни недели | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Мотаж |  | 44 28: 28.10.2019-22.11.2019
2 | ПНР | bar: 47 22 to 48 25
| Подрядчик: _______________________ |  | 44 29: Заказчик: _______________________

## STAND 2007-08-27 CORVUS (hidden)
CORVUS / TMI - PLANING
| Version: | 6.0
| Date: | 13.09.2007
CONFIDENTIAL
SUBJECT TO CHANGE WITHOUT PRIOR NOTICE
[9 empty] | CHRISTMAS BREAK | [8 empty] | CHINESE NEW YEAR
| November 2007 |  |  |  | December 2007 | [5 empty] | January 2008 |  |  |  |  | February 2008 | [5 empty] | March 2008 | [6 empty] | April 2008 |  |  |  |  | May 2008 | [5 empty] | June 2008 |  |  |  |  | July 2008
| KW 46 |  | KW 47 | KW 48 |  | KW 49 | KW 50 | KW 51 | KW 52 | KW 1 |  | KW 2 | KW 3 | KW 4 | KW 5 |  | KW 6 |  | KW 7 | KW 8 | KW 9 |  | KW 10 |  | KW 11 | KW 12 | KW 13 | KW 14 |  | KW 15 | KW 16 | KW 17 | KW 18 |  | KW 19 | KW 20 | KW 21 | KW 21 | KW 22 | KW 23 | KW 24 | KW 25 | KW 26 | KW 27 |  | KW 28
KAI #1
KAI #2
TCO #1
TCO #2
TCO #3
TCO #4
TCO #5
TCO #6
TCO #7
TCO #8
LSS A #1
LSS A #2
LSS A #3
LSS A #4
LSS B #1
LSS B #2
LSS B #3
LSS B #4
LSS B #5
LIA #1/4
LIA #2/4
LIA #3/4
LIA #4/4
CTD/ELA #1/4
CTD/ELA #2/4
CTD/ELA #3/4
CTD/ELA #4/4
GCL - Cleaner
GLM
Laminator 1&2
Laminator 3&4
Laminator 5
VOC 1200
QAC
AOI
GPB
| KW 46 |  | KW 47 | KW 48 |  | KW 49 | KW 50 | KW 51 | KW 52 | KW 01 |  | KW 02 | KW 03 | KW 04 | KW 05 |  | KW 06 |  | KW 07 | KW 08 | KW 09 |  | KW 10 |  | KW 11 | KW 12 | KW 13 | KW 14 |  | KW 15 | KW 16 | KW 17 | KW 18 |  | KW 19 | KW 20 | KW 21 | KW 21 | KW 22 | KW 23 | KW 24 | KW 25 | KW 26 | KW 27 |  | KW 28
| November 2007 |  |  |  | December 2007 | [5 empty] | January 2008 |  |  |  |  | February 2008 | [5 empty] | March 2008 | [6 empty] | April 2008 |  |  |  |  | May 2008 | [5 empty] | June 2008 |  |  |  |  | July 2008
INSTALLATION
INSTALL
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
LINE AUTO.
READY
LIA
TEST
AB 10.03
INSTALL
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
GROUND MEASURING
GROUND MEASURING
GROUND MEASURING
GROUND MEASURING
Start PI
EC
N2
CD
CW
PW
AB,PG,DEZ
INSTALLATION
INSTALLATION
INSTALLATION
INSTALLATION
2
1
2
1
2
1
2
1
2
1
2
1
2
1
2
1
2
1
2
1
1
1
1
1
1
1
1
1
1
1
1
1
PACKAGING
( 2 WEEKS)
1
1
1
1
only Cassettes no installation
1
1
1
1
1
1
1
1
1
1
FACILITY READY REQUEST OERLIKON - CUSTOMER'S RESPONSIBILITY: EQUIPMENT CONNECTED TO: POWER / WATER / CDA / PUMPPIPES / EXHAUST TO ABATMENT / NITROGEN
FACILTIY READY REQUEST OERLIKON - CUSTOMER'S RESPONSIBILITY: EQUIPMENT CONNECTED TO: GAS / ABATMENT
GAS AIR EXTRACTION
MOVE IN - CUSTOMER'S RESPONSIBILITY
SUPERVISION BY OC OERLIKON
2
Process Integration Phase
latestSOP
GROUND MEASURING - CUSTOMER'S RESPONSIBILITY
SUPERVISION BY OC OERLIKON
FACILITY READY - CUSTOMER'S PROPOSAL
OERLIKON RESPONSIBILITY WITH SUPPORT CUSTOMER
Colour Code of Equipment
KAI, TCO, LSS
1 Set of Front end 3rd party Equipment
1 Set fo Back end 3rd party Equipment
1 Set off-line Metrologie
1 Set inline Metrologie